## Sheet1
Gantt Chart
Activity Name | Start | Finish | August | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
|  |  | W-5 | W-1 | W-2 | W-3 | W-4 | W-5 | W-1 | W-2 | W-3 | W-4 | W-5 | W-1 | W-2 | W-3 | W-4 | W-5 | W-1 | W-2 | W-3 | W-4 | W-5
Analysis and Quick Design
Conducted a meeting | 08/23/2021 | 08/23/2021 | bar: August W-5
Brain storming/ Gantt Chart | 08/24/2021 | 08/26/2021 | bar: August W-5
Research for the proposal | 08/23/2021 | 08/27/2021 | bar: August W-5
Creating 3 proposals | 08/24/2021 | 08/28/2021 | bar: August W-5
Presenting the proposals | 08/31/2021 | 08/31/2021 | bar: August W-5
Creating Chapter 1 | 2021-01-09 | 2021-06-09 | bar: September W-1
Creating Admin Log in | 2021-07-09 | 2021-12-09 | bar: September W-2
Creating Dash Board | 09/13/2021 | 09/18/2021 | bar: September W-3
Creating Student Log in | 09/19/2021 | 09/24/2021 | bar: September W-4
Submitting Chapter 1 and revise | 09/25/2021 | 09/26/2021 | bar: September W-4
Creating Chapter 2 | 09/27/2021 | 10/18/2021 | bar: September W-5 to October W-4
Revise Chapter 2 | 10/18/2021 | 10/18/2021
Sumitting Revisse Chapter 2 | 10/19/2021 | 10/30/2021 | bar: October W-4 to October W-5
Creating Chapter 3 | 10/31/2021 | 11/15/2021 | bar: October W-5 to November W-3
Presentation of the System | 11/15/2021 | 11/15/2021 | bar: November W-3
Creating Chapter 4 and Submitting | 11/16/2021 | 11/27/2021 | bar: November W-3 to November W-5
Creating Chapter 5 and Submitting | 11/28/2021 | 2021-09-12 | bar: November W-5 to December W-2
Creating Powerpoint Presentation | 2021-10-12 | 2021-11-12 | bar: December W-2
Defend Of Thesis | 11212/2021 | 2021-12-12 | bar: December W-2